## LEADS_Cost_Management
ID | Name | Start | End | BAC | PV | EV | AC | SV | SPI | CV | CPI | ETC | EAC | VAC | TCPI
101 | Requirements & Competitor Analysis | 4/27/26 | 5/13/26 | 2000 | 2000 | 2000 | 1900 | 0 | 1 | 100 | 1.0526 | 0 | 1900 | 100 | 0
102 | Database Schema & Architecture Design | 5/14/26 | 6/9/26 | 3000 | 3000 | 3000 | 3100 | 0 | 1 | -100 | 0.96774 |  | 3100 | -100 | 0
103 | UI/UX Design | 6/10/26 | 6/23/26 | 2500 | 2500 | 2500 | 2400 | 0 | 1 | 100 | 1.0417 | 0 | 2400 | 100 | 0
104 | SRS & SDS | 6/24/26 | 8/20/26 | 4000 | 4000 | 4000 | 3800 | 0 | 1 | 200 | 1.0526 | 0 | 3800 | 200 | 0
105 | Dev Environment Setup | 8/21/26 | 8/24/26 | 1000 | 1000 | 1000 | 950 | 0 | 1 | 50 | 1.0526 | 0 | 950 | 50 | 0
106 | M01: User Auth & Dual OTP Engine | 8/25/26 | 9/2/26 | 3500 | 3500 | 3200 | 3400 | -300 | 0.91429 | -200 | 0.94118 | 318.75 | 3718.75 | -218.75 | 3
107 | M02: Market Intelligence Engine | 9/3/26 | 9/14/26 | 4500 | 4500 | 4200 | 4600 | -300 | 0.93333 | -400 | 0.91304 | 328.5714 | 4928.5714 | -428.5714 | -3
108 | M03: Scraping Engine (Scrapy Spiders) | 9/15/26 | 9/24/26 | 4000 | 4000 | 3800 | 4100 | -200 | 0.95 | -300 | 0.92683 | 215.7895 | 4315.7895 | -315.7895 | -2
109 | M03: Scraping Engine (Playwright) | 9/25/26 | 10/6/26 | 4500 | 3500 | 3200 | 3600 | -300 | 0.91429 | -400 | 0.88889 | 1462.5 | 5062.5 | -562.5 | 1.4444
110 | M04: Seller Outreach Agent | 10/7/26 | 10/15/26 | 3500 | 2500 | 2200 | 2600 | -300 | 0.88 | -400 | 0.84615 | 1536.3636 | 4136.3636 | -636.3636 | 1.4444
| TOTAL |  |  | 32500 | 30500 | 29100 | 30450 | -1400 | 0.9541 | -1350 | 0.95567 | 3861.9745 | 34311.9745 | -1811.9745 | 1.6585

## Reference_Example
Reference Example (Simple Formulas - Exact Image Match)
Matches the screenshot using direct arithmetic formulas with no IF conditions
ID | Name | Start | End | BAC | PV | EV | AC | SV | SPI | CV | CPI | ETC | EAC | VAC | TCPI
100 | Set up Database | Mar. 1 | Mar. 10 | 10000 | 3000 | 2000 | 4500 | -1000 | 0.66667 | -2500 | 0.44444 | 18000 | 12500 | -2500 | 1.4545
200 | Build Application | Mar. 7 | Mar. 20 | 15000 | 0 | 1500 | 2000 | 1500 | N/A | -500 | 0.75 | 18000 | 15500 | -500 | 1.0385
| TOTAL |  |  | 25000 | 3000 | 3500 | 6500 | 500 | 0.66667 | -3000 | 0.53846 | 36000 | 28000 | -3000 | 1.1622

## Presentation_Guide
Presentation Guide: Simple EVM Formulas for Defense Slides
Metric | Description | Standard Formula | Simple Excel Cell Formula | How to Explain in Presentation
SV | Schedule Variance | EV - PV | 0 | Earned Value minus Planned Value. Positive means ahead, negative means delayed.
SPI | Schedule Performance Index | EV / PV | #DIV/0! | Ratio of work done over scheduled. Above 1.0 is fast, below 1.0 is slow.
CV | Cost Variance | EV - AC | 0 | Earned Value minus Actual Cost. Positive means under budget, negative means overrun.
CPI | Cost Performance Index | EV / AC | #DIV/0! | Cost efficiency. Above 1.0 means efficient, below 1.0 means spending too much.
ETC | Estimate to Complete | (BAC - EV) / CPI | #VALUE! | Remaining budget divided by CPI efficiency. Tells how much more money is needed.
EAC | Estimate at Completion | AC + ETC | 0 | Actual Cost plus remaining ETC. Tells what the task will finally cost.
VAC | Variance at Completion | BAC - EAC | #VALUE! | Original budget minus final estimated cost. Negative means expected deficit.
TCPI | To-Complete Performance Index | (BAC - EV) / (BAC - AC) | #VALUE! | Required efficiency for the rest of the project to meet original budget.